CASA CREADORES

━━━━━━━━━━━━━━━━━━━━

THE GETTING STARTED BIBLE

LATAM's Creator Network for Crypto & Tech Brands

Monthly Budget: $300 Tool Costs: ~$47/mo Buffer: ~$253/mo

This document is your step-by-step operating manual from zero to first revenue.

Read it once end-to-end. Then follow each phase in order.

# How to Use This Document

This is your single operating manual for building and launching Casa Creadores. It is structured into five phases that follow the natural order of building a business: Foundation, then Identity, then Platform, then People, then Revenue.

Each phase has:

- A clear goal — what done looks like

- Step-by-step actions — in the exact order to do them

- Checklists — so nothing gets missed

- Tool links — everything you need is linked

The most important rule: do not jump ahead. Each phase builds on the last. Launching the website before you have creators is a waste of time. Running campaigns before you have tracking set up will cost you data you can never get back. Follow the order.

## The Five Phases at a Glance

| Phase | Name | Goal | When |
| --- | --- | --- | --- |
| 1 | Foundation | Set up all tools, accounts, and infrastructure | Week 1–2 |
| 2 | Identity | Brand, logo, social presence, pitch deck | Week 2–3 |
| 3 | People | Recruit 20–30 founding creators before launch | Week 3–5 |
| 4 | Platform | Build and launch the website + calculator | Week 4–8 |
| 5 | Revenue | Run 3 pilot campaigns, then begin paid outreach | Month 2–3 |

## How to Work With AI Tools (Claude Code, Cowork, Codex)

Your MD files are the blueprint. Every AI session should start by pasting the relevant MD file before giving any instruction. Never ask an AI to build something without first giving it the spec document.

| Task | Files to Paste First | Best Tool |
| --- | --- | --- |
| Website shell + pages | 05_WEBSITE_STRUCTURE + 08_TECH_STACK | Claude Code |
| Calculator build | 06_CALCULATOR + 08_TECH_STACK | Claude Code |
| Creator application page | 03_CREATOR_STRATEGY + 05_WEBSITE_STRUCTURE | Claude Code |
| Brand / campaign pages | 04_BRAND_STRATEGY + 05_WEBSITE_STRUCTURE | Cowork |
| Discord server setup | 07_DISCORD_COMMUNITY | Claude Code |
| Notion workspace setup | 11_OPERATIONS | Cowork |
| API integrations (if stuck) | 06_CALCULATOR section only | Codex as fallback |

Keep a session log in Notion after every build session:

- Date and tool used

- What was built

- What is working and what is deferred

- Files changed

- Next session task

Paste your session log at the start of every new AI session. This replaces the context the AI lost since last time.

| 01 | Foundation Set up every account, tool, and key before writing a line of code — Week 1–2 |
| --- | --- |

Everything in this phase is free or near-free. The goal is to have all your infrastructure accounts created, verified, and ready before you start building anything. Do not skip steps — you will need each of these during the build.

## 1.1 — Development Setup

Do these in order. Each one is required before the next.

| 1 | Create a GitHub account github.com — Free. This is where all your code lives. Every AI tool (Claude Code, Codex) will work from this repo. |
| --- | --- |

| 2 | Install Git on your computer git-scm.com/downloads — Required to push code from your machine to GitHub. |
| --- | --- |

| 3 | Install Node.js (LTS version) nodejs.org — Required to run Next.js locally. Download the LTS (Long Term Support) version. |
| --- | --- |

| 4 | Install VS Code code.visualstudio.com — Your code editor. Free. Install the Tailwind CSS IntelliSense and TypeScript extensions. |
| --- | --- |

| 5 | Create a Vercel account vercel.com — Sign up with your GitHub account. This is where your website will be hosted, for free. |
| --- | --- |

## 1.2 — Domain

| 6 | Buy your domain Namecheap (namecheap.com) or Cloudflare (cloudflare.com/products/registrar). Search for casacreadores.com or casacreadores.io. Aim for .com. Cost: ~$10–15/year. |
| --- | --- |

| 7 | Point domain DNS to Cloudflare cloudflare.com — Free plan. Add your domain to Cloudflare and update the nameservers at Namecheap. Gives you free DDoS protection and fast DNS. |
| --- | --- |

## 1.3 — API Accounts (For the Calculator)

You need four API accounts. All have free tiers sufficient for development and early traffic.

| A | RapidAPI account rapidapi.com — Create one account. This single account gives you access to both the Instagram and TikTok scrapers. Subscribe to the free tier of: (1) Instagram Scraper API at rapidapi.com/social-api1-instagram/api/instagram-scraper-api2 and (2) ScrapTik at rapidapi.com/scraptik-api-scraptik-api-default/api/scraptik |
| --- | --- |

| B | Google Cloud Console (YouTube API) console.cloud.google.com — Sign in with a Google account. Create a new project called 'Casa Creadores'. Go to APIs & Services > Library. Search for 'YouTube Data API v3' and enable it. Go to Credentials > Create Credentials > API Key. Copy and save this key securely. |
| --- | --- |

| C | Twitch Developer Console dev.twitch.tv/console — Sign in with a Twitch account (create one if needed). Go to Applications > Register Your Application. Name: Casa Creadores. OAuth Redirect URL: http://localhost:3000. Category: Website Integration. Copy your Client ID and generate a Client Secret. Save both securely. |
| --- | --- |

Store ALL API keys in a private notes app (not iCloud, not Google Docs). You will paste them into a .env.local file during the website build. Never share them or commit them to GitHub.

## 1.4 — Operations Tools

| D | Create a Notion account notion.so — Free plan. This is your internal command centre: creator roster, campaign tracker, brand pipeline, session logs. You will build the workspace structure in Phase 4. |
| --- | --- |

| E | Create a Metricool account metricool.com — Start on the free plan. You will upgrade to Essential (~$18/mo) when your first paid campaign starts. Metricool is used for UTM link tracking and campaign analytics. |
| --- | --- |

| F | Create a Tally account tally.so — Free plan. You will build your creator application form and brand contact form here. No submission limits on the free tier. |
| --- | --- |

| G | Create a Calendly account calendly.com — Free plan (1 event type). This is your brand discovery call booking link. Set up one 30-minute event type called 'Brand Discovery Call — Casa Creadores'. |
| --- | --- |

| H | Create a Resend account resend.com — Free tier (3,000 emails/mo). This sends your transactional emails (form confirmations, creator welcome emails). |
| --- | --- |

| I | Create a Canva Pro account canva.com — ~$13/mo. Used for campaign reports, pitch decks, and all brand assets. Worth paying for from day one. |
| --- | --- |

## 1.5 — Payment Infrastructure

| J | Set up a crypto wallet for USDT/USDC payments You need to be able to receive and send USDT (TRC-20 recommended — lowest fees). Options: Binance (binance.com) or Trust Wallet (trustwallet.com). This is how you will pay creators and optionally receive payments from crypto-native brands. |
| --- | --- |

| K | Create a Wise account wise.com — For paying creators in Brazil and Mexico via bank transfer. Free to create, fees only on transfers. |
| --- | --- |

## Phase 1 Completion Checklist

☐  GitHub account created

☐  Git + Node.js + VS Code installed

☐  Vercel account created and linked to GitHub

☐  Domain purchased and pointed to Cloudflare

☐  RapidAPI account created, Instagram + TikTok APIs subscribed (free tier)

☐  Google Cloud project created, YouTube Data API v3 enabled, API key saved

☐  Twitch Developer app registered, Client ID + Secret saved

☐  ALL API keys stored securely offline

☐  Notion account created

☐  Metricool account created

☐  Tally account created

☐  Calendly account created, discovery call event set up

☐  Resend account created

☐  Canva Pro active

☐  Crypto wallet set up (USDT capable)

☐  Wise account created

| 02 | Identity Build the brand before building the product — Week 2–3 |
| --- | --- |

Your brand identity must exist before the website is built. The website is built around the brand — not the other way around. This phase is the creative work: logo, colours, typography, tone of voice, and social presence.

## 2.1 — Brand Identity

Casa Creadores is warm, confident, and distinctly LATAM. It should feel like it belongs in Medellín or Buenos Aires — not like a Silicon Valley startup. The name itself means 'House of Creators'. Lean into that — it is a home, a community, a place that belongs to creators.

Use Claude to help generate brand direction, tone of voice, and copy. Use Canva or a designer for the actual logo. Do not use a generic AI logo tool — it will look generic.

### Colour Palette Direction

| Role | Direction | Why |
| --- | --- | --- |
| Primary | Warm terracotta / burnt orange | LATAM warmth, stands out in crypto space dominated by cold blues |
| Secondary | Deep forest green or midnight navy | Trust, credibility, financial space |
| Accent | Warm gold / amber | Premium feel, LATAM richness |
| Background | Off-white / warm cream | Avoids clinical white, feels warm and approachable |
| Text | Near-black (not pure black) | Softer on screen, more considered |

### Typography Direction

- Display / Headlines: A serif with character (Georgia, Playfair Display, or similar) — conveys authority and craft

- Body / UI: A clean geometric sans (not Inter — everyone uses Inter). Consider DM Sans, Plus Jakarta Sans, or Sora.

- Avoid: Inter, Roboto, Arial, generic system fonts

### Tone of Voice

- Confident but not arrogant — you know this market

- Warm but professional — creators and brands both feel welcome

- Direct — no buzzword-heavy agency speak

- Bilingual — Spanish and English used naturally, not as an afterthought

- Grounded in LATAM — specific cultural references, real market knowledge

## 2.2 — Logo

You have three realistic options at this budget:

- Design it yourself in Canva — use Canva's logo maker as a starting point, but customise heavily. Budget 2–3 hours.

- Use a freelancer on Fiverr or Workana (LATAM's Fiverr) — budget $30–$80 for a solid logo. Brief them with your colour direction and tone above.

- Use Claude to generate SVG logo concepts — ask Claude to write SVG code for logo variations based on your brand direction, then iterate.

You need: full colour logo, white version (for dark backgrounds), icon/mark only (for favicon and social profile pics). Minimum formats: PNG (transparent) and SVG.

## 2.3 — Social Media Accounts

Create these accounts before the website launches. Claim your name across platforms now — even if you are not active yet.

| Platform | Handle to Aim For | Priority | Purpose |
| --- | --- | --- | --- |
| X (Twitter) | @casacreadores or @casacreadoresio | High | Brand presence, industry engagement |
| Instagram | @casacreadores | High | Creator community, behind the scenes |
| LinkedIn | Company page: Casa Creadores | High | B2B brand positioning, LinkedIn differentiation story |
| TikTok | @casacreadores | Medium | Creator content, LATAM market presence |

On X and LinkedIn, start posting immediately — even before the site is live. Post about LATAM crypto market trends, creator marketing insights, your perspective on the space. You are building an audience in parallel with building the product.

## 2.4 — Pitch Deck

Build your pitch deck in Canva before you start reaching out to brands. You need it ready before Phase 5. Structure (8–10 slides):

- The Problem — crypto/tech brands cannot reach LATAM authentically

- The Market — LATAM crypto adoption stats, size, growth

- Our Solution — Casa Creadores in one sentence

- Our Network — creator roster (real founding cohort numbers), platforms, countries

- The LinkedIn Difference — why LinkedIn UGC in LATAM is untapped for B2B

- How It Works — brief to creators to results in 3 steps

- Campaign Packages — Spark / Fuego / Escala with pricing

- Case Studies — use pilot data when available, or clearly labelled projections

- The Team — you and your partner, why you

- Next Step — book a call CTA

## Phase 2 Completion Checklist

☐  Colour palette defined and documented

☐  Typography choices made

☐  Tone of voice written down (3–5 sentences you can reference)

☐  Logo created (full colour, white, icon versions)

☐  Logo exported as PNG (transparent) and SVG

☐  X account created and profile complete

☐  Instagram account created and profile complete

☐  LinkedIn company page created

☐  TikTok account created

☐  First 3 posts live on X and LinkedIn

☐  Pitch deck built in Canva (even draft version)

| 03 | People Recruit your founding creator cohort before the website exists — Week 3–5 |
| --- | --- |

This is the most important phase and the one most founders skip. Do not launch a creator platform with zero creators. Your business partner leads this phase. The goal is 20–30 vetted, excited founding creators ready to go before the site launches.

The chicken-and-egg problem kills two-sided marketplaces. You solve it by building supply before you have demand. Brands see a real roster on day one. This is non-negotiable.

## 3.1 — Who to Recruit

Focus on these creator profiles for your founding cohort. Quality over quantity — 20 right creators beats 100 wrong ones.

| Profile | Platforms | Why They Matter |
| --- | --- | --- |
| LATAM crypto educators (Spanish) | X, Instagram, YouTube | Core niche, high brand relevance |
| LATAM crypto educators (Portuguese) | Instagram, TikTok, YouTube | Brazil market — distinct from Spanish LATAM |
| Fintech / personal finance creators | Instagram, TikTok, LinkedIn | Broader audience, less niche-risky |
| LinkedIn fintech professionals | LinkedIn only | Your key differentiator — B2B gold |
| Female crypto creators | Instagram, TikTok | Underserved, high engagement, unique brand value |
| Startup / entrepreneur creators | LinkedIn, X, Instagram | Bridges crypto and B2B tech audiences |

For LinkedIn: do not require large follower counts. A 1,500-follower LinkedIn professional in fintech in Bogota with 3% engagement is more valuable to a B2B brand than a 50K Instagram follower with 0.8% ER.

## 3.2 — How to Find Them

- X/Twitter: search crypto + Spanish/Portuguese + location keywords. Example: 'cripto Argentina', 'DeFi Mexico', 'bitcoin Brasil'

- Instagram: search hashtags like #criptolatam, #bitcoinargentina, #finanzaspersonales, #criptobrasil

- TikTok: same hashtag approach — TikTok has a huge growing crypto creator base in LATAM

- LinkedIn: search 'fintech' + Colombia/Argentina/Mexico/Brazil, filter by people, look for 500–5,000 follower range with active posting

- YouTube: search Spanish/Portuguese crypto content — smaller channels (5K–50K subs) are ideal

- Your network: both of you ask anyone in crypto/tech LATAM circles who creates content

## 3.3 — The Outreach Message

Keep it short, personal, and specific. Mention something real about their content. Do not use a generic template blast.

Sample DM (adapt per creator): "Hola [Name], vi tu post sobre [specific topic] — muy bueno. Estoy lanzando Casa Creadores, una red de creadores LATAM especializada en cripto y tech. Conectamos creadores con marcas que quieren llegar a audiencias latinoamericanas de forma auténtica. Me gustaría invitarte como creador fundador — sin costo, con acceso prioritario a campañas de marcas. ¿Te llama la atención?"

## 3.4 — The Vetting Process

Before adding anyone to the founding cohort, verify these minimums:

☐  Public profile on at least one platform

☐  Content is in Spanish or Portuguese (or bilingual)

☐  50%+ of content is tech, crypto, finance, or entrepreneurship related

☐  Engagement rate meets minimum: 3% for nano (1K–10K), 1.5% for micro (10K–100K)

☐  No promotion of obvious scam projects in their history

☐  Has a payment method (crypto wallet OR bank account)

☐  Responds to DMs and seems reliable

Use HypeAuditor's free audit feature (hypeauditor.com) to spot fake followers before adding anyone to the roster. One free audit check per account.

## 3.5 — Onboarding Founding Creators

Once a creator says yes, send them a simple welcome message with these three things:

- What Casa Creadores is (2 sentences)

- What being a founding creator means (featured on site, priority deals, free Discord access)

- The application form link (Tally form — build this in Phase 4) so you have their structured data

You can send people the Tally form link before the website exists. Create the form in Tally first (Phase 4 Step 1) and share the direct Tally link via DM.

## 3.6 — Track Them in Notion

As you recruit, track every creator in your Notion Creator Roster database (set up in Phase 4). For now, even a simple spreadsheet works temporarily. Fields to capture immediately:

- Full name + country

- All platform handles + follower counts

- Engagement rate (calculate manually or use the calculator once built)

- Primary niche

- Payment preference

- Status: Interested / Applied / Approved

## Phase 3 Completion Checklist

☐  Identified 40–50 potential creators across target profiles

☐  Sent personalised outreach to all identified creators

☐  20+ creators have said yes and been vetted

☐  All 20+ have completed the application form (or given you their data directly)

☐  All 20+ tracked in Notion/spreadsheet with handles, followers, ER

☐  At least 3 LinkedIn-specific creators in the founding cohort

☐  At least 3 Portuguese-language (Brazil) creators in the founding cohort

☐  Payment details collected from all founding creators

| 04 | Platform Build and launch the website, calculator, and Notion workspace — Week 4–8 |
| --- | --- |

This is the longest phase technically, but your MD files make it straightforward. You are handing 06_CALCULATOR.md and 05_WEBSITE_STRUCTURE.md to Claude Code and building feature by feature. Do not try to build everything at once.

## 4.1 — Notion Workspace (Do This First)

Set up Notion before the website so you have a place to capture creator and brand data as it comes in. This takes 1–2 hours.

To build this: open a Claude Code or Cowork session, paste 11_OPERATIONS.md, and ask it to write out the exact Notion database schemas with all properties. Then build them in Notion manually — it takes minutes once you have the spec.

☐  Creator Roster database created (all properties from 11_OPERATIONS.md)

☐  Brand Pipeline database created (all properties)

☐  Campaign Tracker database created (all properties)

☐  Folder structure created (Campaigns, Creators, Brands, Reporting, Resources)

☐  All 12 MD files uploaded to Resources folder

☐  Session log template created

## 4.2 — Tally Forms (Do This Second)

Build both forms before the website so you can share direct Tally links during Phase 3 outreach.

| 1 | Creator Application Form Fields from 03_CREATOR_STRATEGY.md — Section 'Application Form Fields'. Build in Tally. Connect email notifications to your inbox. Copy the direct Tally link for DM outreach. |
| --- | --- |

| 2 | Brand Campaign Brief Form Fields from 04_BRAND_STRATEGY.md — Section 'Option 2 Email Us'. Build in Tally. This goes on the website contact page. |
| --- | --- |

## 4.3 — Website Build

Follow this exact build order. Complete and test each step before moving to the next. Use Claude Code for every step.

Session prompt template for every build session: 'I am building Casa Creadores — a LATAM UGC creator network for crypto/tech brands. Here is my tech stack: [paste 08_TECH_STACK.md]. Here is today's feature: [paste relevant MD section]. Existing code: [paste files]. Today's task: [one specific thing].'

### Step-by-Step Build Order

| Step | Task | Files to Paste | Est. Time |
| --- | --- | --- | --- |
| 1 | Init Next.js project with TypeScript + Tailwind | 08_TECH_STACK.md | 30 min |
| 2 | Connect GitHub repo to Vercel, add domain | 08_TECH_STACK.md | 30 min |
| 3 | Build layout: navbar, footer, global styles | 05_WEBSITE_STRUCTURE.md | 2–3 hrs |
| 4 | Build homepage (static content, no APIs) | 05_WEBSITE_STRUCTURE.md | 3–4 hrs |
| 5 | Build For Brands page | 04_BRAND_STRATEGY.md + 05 | 2 hrs |
| 6 | Build For Creators page | 03_CREATOR_STRATEGY.md + 05 | 2 hrs |
| 7 | Build Contact page (Calendly embed + Tally form) | 05_WEBSITE_STRUCTURE.md | 1 hr |
| 8 | Build creator application page (Tally embed) | 05_WEBSITE_STRUCTURE.md | 1 hr |
| 9 | Build calculator UI (tabs + input + results card, no APIs yet) | 06_CALCULATOR.md | 4–5 hrs |
| 10 | Connect YouTube API to calculator | 06_CALCULATOR.md — YouTube section | 2–3 hrs |
| 11 | Connect Twitch API to calculator | 06_CALCULATOR.md — Twitch section | 2–3 hrs |
| 12 | Connect RapidAPI (Instagram) | 06_CALCULATOR.md — Instagram section | 2–3 hrs |
| 13 | Connect RapidAPI (TikTok) | 06_CALCULATOR.md — TikTok section | 2–3 hrs |
| 14 | Connect RapidAPI (X/Twitter) | 06_CALCULATOR.md — X section | 2–3 hrs |
| 15 | Build LinkedIn manual input mode | 06_CALCULATOR.md — LinkedIn section | 1–2 hrs |
| 16 | Add rate limiting + caching to API routes | 06_CALCULATOR.md — Backend section | 1–2 hrs |
| 17 | Add Google Analytics 4 | 08_TECH_STACK.md | 30 min |
| 18 | Mobile responsiveness pass | All pages | 2–3 hrs |
| 19 | Final content pass (copy, creator profiles, stats) | 05_WEBSITE_STRUCTURE.md | 2–3 hrs |
| 20 | Launch — point domain, announce on X and LinkedIn | — | 1 hr |

## 4.4 — Discord Server

Set up Discord in parallel with the website build. It does not need to wait for the website to launch.

| 1 | Create the Discord server discord.com — Create a new server called 'Casa Creadores'. Use your logo as the server icon. |
| --- | --- |

| 2 | Build the channel structure Follow the exact structure in 07_DISCORD_COMMUNITY.md — Section 'Server Structure'. Create all channels in order. |
| --- | --- |

| 3 | Install MEE6 bot mee6.xyz — Add to your server. Configure welcome message for new members in #welcome. Set up auto-role for verified creators. |
| --- | --- |

| 4 | Set up Whop for paid tier whop.com — Create a product called 'Casa Insider'. Price: $15/mo. Connect to your Discord server. Whop will handle payment and automatic role assignment. |
| --- | --- |

| 5 | Invite founding creators Send Discord invite link to all 20+ founding creators from Phase 3. Give them the Founding Creator role manually. Make it feel alive before it opens publicly. |
| --- | --- |

## 4.5 — Add Your .env.local File

Before testing the calculator, create your environment variables file. This goes in the root of your Next.js project and must never be committed to GitHub.

# .env.local — NEVER commit this file to GitHub RAPIDAPI_KEY=your_rapidapi_key_here YOUTUBE_API_KEY=your_google_api_key_here TWITCH_CLIENT_ID=your_twitch_client_id_here TWITCH_CLIENT_SECRET=your_twitch_client_secret_here RESEND_API_KEY=your_resend_key_here

Also add these same variables to your Vercel project settings under Settings > Environment Variables. This is how the live site accesses them.

## Phase 4 Completion Checklist

☐  Notion workspace fully built

☐  Both Tally forms live and tested

☐  Next.js project initialised and deployed to Vercel

☐  Custom domain pointing to Vercel

☐  All website pages built and live

☐  Calculator working for all 6 platforms

☐  All API keys in .env.local AND Vercel env variables

☐  Google Analytics 4 connected

☐  Site is mobile-responsive

☐  Discord server live with full channel structure

☐  Whop paid tier set up

☐  20+ founding creators in Discord

☐  Launch announced on X and LinkedIn

| 05 | Revenue 3 pilot campaigns then paid brand outreach — Month 2 onwards |
| --- | --- |

The website is live. Creators are in Discord. Now you build the proof that the business works. Run three pilot campaigns — free or near-free — and generate the case study data that makes every future brand conversation easier.

## 5.1 — Finding Your 3 Pilot Brands

Your 3 pilot clients should be:

- Brands you already have a connection to, or can reach directly

- Small to medium crypto/tech projects — not huge enterprises who expect polished operations

- Willing to share results data with you for use in case studies (get this in writing)

- Ideally in different sub-niches so your case studies demonstrate range

Frame the pilot offer honestly: 'We are launching Casa Creadores and running our first 3 campaigns at cost/free to build case studies. In exchange we ask for your honest feedback and permission to use results in our portfolio.' Most early-stage crypto brands will say yes.

## 5.2 — Running Your First Campaign (Spark)

Every campaign, however small, follows the same process. Use the checklist from 10_CAMPAIGN_TRACKING.md and 11_OPERATIONS.md. Here is the simplified flow:

| 1 | Complete campaign brief Brand fills in the Tally brief form. You review and confirm deliverables, platform, creator count, timeline, and goal. |
| --- | --- |

| 2 | Create UTM links One unique UTM link per creator per platform. Use Bitly or Google's UTM builder. Log all links in Notion campaign tracker. |
| --- | --- |

| 3 | Match and brief creators Select 5 creators from your founding cohort that match the brand's audience. Send them a creator brief (Word doc or Google Doc): brand background, key messages, prohibited claims, disclosure requirements (#ad/#publicidad), UTM link, deadline. |
| --- | --- |

| 4 | Content review (optional) For pilot campaigns especially: ask creators to share draft content before posting. One round of feedback. This builds trust and improves quality. |
| --- | --- |

| 5 | Posts go live Track in Notion: tick off each post as it goes live. Monitor UTM clicks in Bitly. |
| --- | --- |

| 6 | Collect metrics Creators submit post URL + analytics screenshot via Tally form within 24hrs of posting. |
| --- | --- |

| 7 | Build and send report Use Canva campaign report template. Structure from 10_CAMPAIGN_TRACKING.md. Send within 5 business days of campaign end. |
| --- | --- |

| 8 | Pay creators 50% was paid on brief confirmation (or on content approval for pilots). Pay remaining 50% within 7 days of campaign end. Use USDT or Wise. |
| --- | --- |

## 5.3 — Paid Brand Outreach

Once you have one completed pilot with real data, begin paid outreach. Do not wait for all three pilots — start outreach after the first.

### Who to Contact

| Source | What to Look For | How to Find Them |
| --- | --- | --- |
| CoinMarketCap / CoinGecko | Exchanges + projects with Spanish social accounts | Filter by LATAM region or Spanish-language Twitter |
| LinkedIn | 'Head of Marketing' + 'crypto' + LATAM country | LinkedIn search — connect then DM |
| Twitter/X crypto communities | Brands already posting in Spanish but badly | Search hashtags, see who the brands are |
| Crunchbase / AngelList | Funded LATAM fintech startups | Filter by country + category |
| Your own network | Anyone in crypto/tech who has a brand to promote | Direct ask |

### Outreach Volume Target

20 personalised outreach messages per week minimum. At a 5% positive response rate (conservative for a warm, relevant pitch) that is 1 new brand conversation per week. At a 20% close rate from conversations, you close 1 brand per month.

Track every single outreach message in your Brand Pipeline Notion database. Date, platform, message sent, response, next step. Without tracking, you lose momentum and cannot improve your conversion rate.

## 5.4 — Pricing Conversations

When a brand asks your prices, lead with value then price. Never lead with price.

| Package | What You Say | Price |
| --- | --- | --- |
| Spark | 5 trusted LATAM crypto voices, your platform, 2 weeks, full analytics report | $500–$800 |
| Fuego | 15 creators, 2–3 platforms, 30 days, mid + end reports, mixed tiers | $1,500–$2,500 |
| LinkedIn Add-on | 5 LinkedIn professionals in your niche — B2B decision-maker reach | $300–$500 |
| Escala / Retainer | Ongoing partnership — custom brief, we match to your goals monthly | From $1,500/mo |

If a brand pushes back on price, do not immediately discount. Ask what their budget is first. Then propose a reduced-scope Spark rather than discounting the same deliverable. Scope down, not price down.

## 5.5 — Discord Revenue (Month 3+)

Once the Discord has 20+ founding creators active and posting, open the paid Founding Member tier. Create urgency: first 50 spots at $10/mo for life. Promote to:

- All approved creators not yet in Discord

- Creators who used the calculator tool (via thank-you page CTA)

- Your social following on X and Instagram

At 50 paid members at $10/mo: $500/mo in recurring revenue. This alone covers your entire operating cost.

## 5.6 — Monthly Operating Rhythm

Once revenue is flowing, run this rhythm every month:

| Week | Focus | Key Actions |
| --- | --- | --- |
| Week 1 | Outreach + pipeline | 20 brand outreach messages, follow up on open conversations, review Brand Pipeline |
| Week 2 | Campaign execution | Active campaigns: collect posts, monitor UTMs, mid-campaign update to any active brands |
| Week 3 | Reporting + community | Send campaign reports for completed work, post LATAM Creator Brief to Discord, recruit 2–3 new creators |
| Week 4 | Review + plan | Review what worked, update pricing if needed, plan next month's outreach targets |

## Phase 5 Completion Checklist

☐  3 pilot campaign brands identified and agreed

☐  First pilot campaign briefed, creators assigned

☐  UTM links created for all campaigns

☐  All creator briefs sent with compliance requirements

☐  Posts live and metrics being collected

☐  First campaign report delivered to client

☐  First creator payouts sent

☐  Case study data documented (with brand permission)

☐  Paid outreach begun (20 messages/week)

☐  Brand Pipeline active with 10+ prospects tracked

☐  Discord paid tier launched

# Quick Reference

## All Tool Links

| Tool | URL | Purpose | Cost |
| --- | --- | --- | --- |
| GitHub | github.com | Code repository | Free |
| Vercel | vercel.com | Website hosting | Free |
| Namecheap | namecheap.com | Domain purchase | ~$12/yr |
| Cloudflare | cloudflare.com | DNS + security | Free |
| RapidAPI | rapidapi.com | IG + TikTok + X scrapers | Free tier |
| Instagram Scraper | rapidapi.com/social-api1-instagram/api/instagram-scraper-api2 | Instagram data | 500 req free |
| ScrapTik (TikTok) | rapidapi.com/scraptik-api-scraptik-api-default/api/scraptik | TikTok data | Free tier |
| Google Cloud | console.cloud.google.com | YouTube API key | Free |
| Twitch Dev | dev.twitch.tv/console | Twitch API credentials | Free |
| Notion | notion.so | Internal ops + CRM | Free |
| Metricool | metricool.com | Campaign analytics | ~$18/mo |
| Tally | tally.so | Forms (creator + brand) | Free |
| Calendly | calendly.com | Brand call booking | Free |
| Resend | resend.com | Transactional email | Free |
| Canva Pro | canva.com | Reports + pitch deck | ~$13/mo |
| Discord | discord.com | Creator community | Free |
| Whop | whop.com | Paid Discord gating | Free + % |
| Binance | binance.com | USDT creator payments | Free |
| Wise | wise.com | Bank transfer payments | Per transfer |
| HypeAuditor | hypeauditor.com | Creator fraud check | Free (limited) |
| Bitly | bitly.com | UTM link tracking | Free |

## Key Formulas

| Platform | Engagement Rate Formula | Notes |
| --- | --- | --- |
| Instagram | (avg likes + avg comments) / followers × 100 | Use median of last 12 posts |
| TikTok | (avg likes + avg comments + avg shares) / followers × 100 | Use median of last 12 videos |
| YouTube | (avg likes + avg comments) / avg views × 100 | Views-based, not subscribers |
| X (Twitter) | (avg likes + avg reposts + avg replies) / followers × 100 | Use median of last 10 posts |
| Twitch | avg concurrent viewers / followers × 100 | Live data only |
| LinkedIn | (avg likes + avg comments) / followers × 100 | Self-reported — manual mode |

## Engagement Rate Benchmarks — Instagram

| Followers | Excellent | Good | Average | Below Avg | Poor |
| --- | --- | --- | --- | --- | --- |
| 1K–10K | >7% | 4–7% | 2–4% | 1–2% | <1% |
| 10K–100K | >3.5% | 2–3.5% | 1–2% | 0.5–1% | <0.5% |
| 100K–500K | >2.5% | 1.5–2.5% | 0.8–1.5% | 0.4–0.8% | <0.4% |
| 500K+ | >2% | 1–2% | 0.5–1% | 0.3–0.5% | <0.3% |

## Campaign Pricing at a Glance

| Package | Creators | Posts | Duration | Price | Our Margin (30%) |
| --- | --- | --- | --- | --- | --- |
| Spark | 5 | 5 total | 2 weeks | $500–$800 | $150–$240 |
| Fuego | 15 | 30 total | 4 weeks | $1,500–$2,500 | $450–$750 |
| LinkedIn Add-on | 5 | 5 LinkedIn | Per campaign | $300–$500 | $90–$150 |
| Escala / Retainer | 30+ | Custom | Ongoing | From $4,000 | Negotiated |

## MD Files Reference

| File | When to Use It |
| --- | --- |
| 01_BUSINESS_MODEL.md | Revenue model questions, pricing decisions, stage planning |
| 02_TARGET_MARKET.md | Brand outreach targeting, creator profile selection |
| 03_CREATOR_STRATEGY.md | Creator recruitment, vetting, contracts, payments |
| 04_BRAND_STRATEGY.md | Brand outreach, proposals, campaign packages |
| 05_WEBSITE_STRUCTURE.md | Any website build session with Claude Code |
| 06_CALCULATOR.md | Calculator build sessions — paste full file for API work |
| 07_DISCORD_COMMUNITY.md | Discord setup, paid tier, community management |
| 08_TECH_STACK.md | Start of every build session — gives AI the full stack context |
| 09_COMPLIANCE_NOTES.md | Before every campaign — crypto content rules per country |
| 10_CAMPAIGN_TRACKING.md | Setting up UTMs, Metricool, building reports |
| 11_OPERATIONS.md | Notion setup, weekly rhythm, campaign checklists |

## Emergency Contacts & Fallbacks

| Situation | What to Do |
| --- | --- |
| Instagram API goes down / breaks | Try alternate on RapidAPI: instagram-api-fast-reliable-data-scraper. Show user-friendly error message in calculator UI. |
| TikTok API goes down | ScrapTik has status page at scraptik.com. Try alternate RapidAPI TikTok provider. Cache last known result if available. |
| RapidAPI free quota hit | Upgrade Instagram scraper to $15/mo plan (30K req). TikTok free tier is separate — upgrade independently. |
| YouTube quota hit (10K units/day) | Apply for quota extension in Google Cloud Console. Temporarily cache results for 48hrs to reduce usage. |
| Creator misses campaign deadline | Contact immediately. Give 24hr grace. If still missed: replace with standby creator from roster. Document in campaign notes. |
| Brand disputes results | Pull all data: UTM click report, creator screenshots, Metricool export. Present transparently. Offer partial credit on next campaign if genuinely poor. |

# Session Log Template

Copy this template into Notion for every AI build session. Paste the previous session's log at the start of each new session.

CASA CREADORES — BUILD SESSION LOG Date: _______________ Tool used: ☐ Claude Code ☐ Cowork ☐ Codex ☐ Claude.ai MD files referenced: _______________ WHAT WAS BUILT THIS SESSION: _________________________________________________________________ WHAT IS WORKING: _________________________________________________________________ WHAT IS BROKEN / DEFERRED: _________________________________________________________________ FILES CHANGED (list filenames): _________________________________________________________________ NEXT SESSION TASK: _________________________________________________________________

## Master Checklist — Zero to Launch

### Phase 1 — Foundation

☐  GitHub, Git, Node.js, VS Code installed

☐  Vercel account linked to GitHub

☐  Domain purchased + Cloudflare DNS

☐  RapidAPI account + Instagram + TikTok APIs subscribed

☐  Google Cloud project + YouTube API key

☐  Twitch Developer app + credentials

☐  ALL API keys saved securely

☐  Notion, Metricool, Tally, Calendly, Resend, Canva Pro accounts

☐  Crypto wallet (USDT) + Wise account

### Phase 2 — Identity

☐  Colour palette + typography defined

☐  Logo created (3 versions: full, white, icon)

☐  X, Instagram, LinkedIn, TikTok accounts live

☐  First posts on X and LinkedIn

☐  Pitch deck drafted in Canva

### Phase 3 — People

☐  20+ vetted founding creators recruited

☐  3+ LinkedIn creators in cohort

☐  3+ Portuguese-language (Brazil) creators in cohort

☐  All creators in Notion roster with handles, ER, payment info

### Phase 4 — Platform

☐  Notion workspace fully built

☐  Tally creator application form live

☐  Tally brand brief form live

☐  Website built and deployed to Vercel with custom domain

☐  Calculator working for all 6 platforms

☐  Google Analytics 4 connected

☐  Discord server live with full structure

☐  20+ founding creators in Discord

☐  Whop paid tier set up

☐  Launch announced

### Phase 5 — Revenue

☐  3 pilot brands identified and agreed

☐  All 3 pilot campaigns run with UTM tracking

☐  3 campaign reports delivered

☐  3 case studies documented

☐  Paid outreach begun — 20 messages/week

☐  10+ brands in Notion pipeline

☐  First paid campaign closed

☐  Discord paid tier launched

☐  First creator payouts sent